## Schedule
Week | Date | Milestones | Mark
1 | 2021-01-15 | Roles and responsibilities / GitHub setup | 0
2 | 2021-01-22 | Game story line and characters | 0
3 | 2021-01-29 | General Storyline / world map | 5
4 | 2021-02-05 | Structural data files - dynamic vs static | 5
5 | 2021-02-12 | Architecture map | 5
6 | 2021-02-19 | UML class diagram | 5
7 | 2021-02-26 | UML state diagram | 5
8 | 2021-03-05 | Code, test, debug | 0
9 | 2021-03-12 | Code, test, debug | 0
10 | 2021-03-19 | Design patterns - alpha version codebase | 5
11 | 2021-03-26 | Demonstration - User POV | 10
12 | 2021-04-02 | Demonstration - Programmer POV | 20
|  | Total Project Mark | 60
Formulas:
Date = [Date, row above]+7

## Requirements and Functionality
Gameplay
Turn based
game world is graph structure where nodes are called rooms
Each room has long / short description
Long description supplied when entering room for first time (or when called)
edges correspond to directions
Each turn - print what player sees and prompts users to enter command
Command parser recognize simple commands
No combat required
Technical Requirements
Design must be object-oriented fashion
Must have official style guide
Must read from standard input and print to standard output
**If random, hardcode seed value of RNG
Only use standard library
Must contain automated unit tests for every function (must reach 100% statemetn coverage)
Mandatory Functionality
Command parser must recognize and handle 6 verbs (N,S,E,W don't count)
At least eight rooms
At least ten passive items to make meaningful changes to gameworld
Must feature at least two NPCs (non-playable characters)
All characters act once per turn (including NPCs, regardless of location)
Nice-to-Have Functionality
Use SOLID or GRASP design principles
Describe multiple items as a coherent paragraph and not disjoint sentences
Use variable phrasing to make text more natural
Ability to save and restart at a later time
God's eye mode / cheat mode
Control other characters (including NPCs)
Special items that impact gameplay
Data structures that allow nesting of items and characters inside each other